## Slide 1
Master in Smart Transport and Logistics for Cities / SmaLog
WP 10.2 Coordination Meetings of the PMC (6th)
Current status and final remarks for completing activities
23th March 2021, 9:00 – 12:00
on line – MS Teams Platform
KA2 - Cooperation for innovation and the exchange of good practices
Capacity Building in Higher Education
Joint project
Antonio Comi
comi@ing.uniroma2.it
University of Rome
Tor Vergata
Italy
Department of Enterprise Engineering

## Slide 2: Programme at a glance
Objectives
  Share the advancement in the activities of each WP
  The road to the end of eligibility period, 14th of October 2021
    Final reports
      Report on partner activity according to staff costs and travel costs, equipment costs
      Deliverables for Project dissemination: i.e. reports of activities developed within each wps (deliverables): currently only wp2 deliverables have been finalised
      Final report to Submit to EACEA
    Budget overview: Grant and SMS
    How to continue after eligibility period: new proposals?

## Slide 3: Schedule 1
Time | Topic | Speaker(s)
09:00-09:15 | Greetings Introduction to the meeting | Antonio Comi (UNITOV)
09:15-09:45 | WP 3 “Theoretical fundamentals of PhD Programme in SmaLog”: current status and final remarks | Anastasia Azarko (UNIROMA1)
 | WP 7 “International Quality Assurance System”: current status and final remarks | Umberto Crisalli (UNITOV) Dmitry Roslavtsev (NUUE)
 | WP 6 “Pilot Smalog students’ training”: current status and final remarks | Mariia Olkhova (NUUE)
09:45-10:15 | WP 4 “System of UA/GE University of SmaLog teachers’ skills upgrading”: current status and final remarks | Olga Kunytskaya (NTU)
 | WP 8 “Project Quality Control and Monitoring”: current status and final remarks | Anastasia Azarko (UNIROMA1)
 | WP 9 “Dissemination and Exploitation activities of the Project”: current status and final remarks | Mykola Zhuk (LPNU)

## Slide 4: Schedule 2
Time | Topic | Speaker(s)
10:15-11:00 | WP 5 “Methodical, Organizational and technical support of SmaLog students’ training”: current status and final remarks | Vasyl Mamray (ZSTU)
 | Special Mobility Strand | Kateryna Vakulenko (NUUE)
11:00-11:30 | WP 10 “Project management ……”: Final reports Report on partner activity according to staff costs and travel costs, equipment costs Deliverable for Project dissemination Final report to Submit to EACEA Budget overview: Grant and SMS How to continue after eligibility period: new proposals? | Antonio Comi (UNITOV)
 | Closing keynotes (open discussion) | 

## Slide 6: WP 10 “Project management ……”
Final reports
  Report on activities developed according WP plans and to staff costs and travel costs, equipment costs
  Deliverable for Project dissemination
  Final report to Submit to EACEA
Budget overview: Grant and SMS
How to continue after eligibility period: new proposals?

## Slide 7: WP 10 “Project management ……” A.i Report on activities developed
It is required by EACEA for proving the costs supported with activities developed.
Each partner is important that stores the outcomes in order that they can be available when EACEA will asks for deeping.
The report of developed activities is organised as follows:
  A chapter for each WP. For example:
    Chapter 1 – Consolidated Work Plan (Preparation)
      Section 1.1 Initial workshops in Partners Countries
      Section 1.2 Setting up of agreement with Participants
      Section 1.3 Initial Conference of Project Participants
    …….
    Each section should be as short as possible. For e.g. minimum half a page and not longer than 4/5 pages.
    Include the people involved as well as the travels performed according to the costs declared by each institution.
    The Template will be soon provided.

## Slide 8: WP 10 “Project management ……” A.i Report on activities developed
Deadline
Template available before 5th of April 2021
Completed WPs: June 2021

## Slide 9: WP 10 “Project management ……” A.ii Deliverable for Project dissemination
CV development: quite all published in final version (to be completed GTU, BSMA. Deadline: March 2021)
International Quality Assurance System (IQAS). Advanced version published. To update and to prepare the final version. Deadline: April 2021
Quality Plan: first version published. To update and to prepare the final version. Deadline: July 2021
Dissemination and exploitation plan: first version to be published. To update and to prepare the final version. Deadline: July 2021
Staff teaching materials: quite completed in final version (Moodle platform)
Student learning/training material. Under development. Deadline: July 2021
Website and Final Conference in Kharkiv, Sept 2021 or ON-LINE(?)

## Slide 10: WP 10 “Project management ……” A.iii Final report to Submit to EACEA 1
The Technical Implementation Report is a contractual obligation
Intermediate result: GOOD (between 74 and 60 pts out of 100)
projects falling into the category "weak" (scoring between 0 and 50) will be subject to a reduction of the EU contribution in accordance with the Grant Agreement, Article I.10.6.

## Slide 11: WP 10 “Project management ……” A.iii Final report to Submit to EACEA 2
Annexes to be attached electronically to the Technical eReport:
Financial Statements (all partners)
Declaration of honour (coordinator)
Table of achieved / planned results (all WP leaders)
Dissemination plan (WP9)
Quality assurance plan (WP7/WP8)
Report on the “Special Mobility Strand” (all partners)

## Slide 12: WP 10 “Project management ……” B. Budget overview 1
GRANT – ANNEX III

## Slide 13: WP 10 “Project management ……” B. Budget overview 2
GRANT – ANNEX III

## Slide 14: WP 10 “Project management ……” B. Budget overview - SPENT 3
Budget headings | Est. Num of beneficiaries | REAL Num of beneficiaries | Est. Budget | REAL Budget
Staff from Partner Countries | 48 | 39 | € 246,046.00 | € 194,135.00
Staff from Programme Countries | 32 | 13 | € 65,436.00 | € 29,192.00
Students from Partner Countries | 60 | 66 | € 286,400.00 | € 240,038.00
Students from Programme Countries | 0 |  |  | 
Grant for Special Mobility Strand |  |  | € 597,882.00 | €463,365.00
Travels are not an weaknesses - but activities should be DONE
through e-learning/e-training
SMS GRANT

## Slide 15: WP 10 “Project management ……” B. Budget overview - SPENT 4
 | TOTAL STAFF AND STUDENT - GRANT | TOTAL STAFF AND STUDENT - SPENT | AVAILABLE
UNITOV | 10,372.00 € | 5,430.00 € | 4,942.00 €
UNISAPIENZA | 8,540.00 € | - € | 8,540.00 €
NUUE | 98,030.00 € | 98,030.00 € | - €
LPNU | 90,201.00 € | 89,659.00 € | 542.00 €
ZSPU | 95,861.00 € | 82,476.00 € | 13,385.00 €
NTU | 102,051.00 € | 94,835.00 € | 7,216.00 €
GTU | 93,636.00 € | 43,141.00 € | 50,495.00 €
BSMA | 52,667.00 € | 26,032.00 € | 26,635.00 €
SUT | 31,504.00 € | 23,762.00 € | 7,742.00 €
IMPEER | - € | - € | - €
HSW | 15,020.00 € | - € | 15,020.00 €
 | 597,882.00 € | 463,365.00 € | 134,517.00 €
SMS GRANT
We received € 538,094 from EACEA.
Currently, we have to return € 74,729 (i.e. € 538,094 - € 463,365)

## Slide 16: WP 10 “Project management ……” B. Budget overview – SMS Students 5
 |  | student mobility - GRANT |  | student mobility - DONE | 
 |  | num. beneficiaries | Budget | num. beneficiaries | Budget
P01 | UNITOV |  |  |  | 
P02 | UNISAPIENZA |  |  |  | 
P03 | NUUE | 9 | €56,934.00 | 14 | €57,326.00
P04 | LPNU | 9 | €49,635.00 | 15 | €54,323.00
P05 | ZSPU | 17 | €55,105.00 | 17 | €47,287.00
P06 | NTU | 10 | €61,295.00 | 13 | €54,177.00
P07 | GTU | 10 | €52,200.00 | 5 | €22,325.00
P08 | BSMA | 5 | €11,231.00 | 2 | € 4,600.00
P09 | SUT |  |  |  | 
P10 | IMPEER |  |  |  | 
P11 | HSW |  |  |  | 
 |  |  | € 286,400.00 |  | € 240,038.00
 | PC |  | € 286,400.00 |  | € 240,038.00
 | ProgC |  | € - |  | € -
CONCLUDED
SAVINGS = 46,362.00 €
Contractual obligations RESPECTED

## Slide 17: WP 10 “Project management ……” B. Budget overview – SMS Staff 6
 |  | Staff mobility - GRANT |  | Staff mobility - DONE |  | Staff mobility - TO DO |  | Staff mobility - FORECAST TO THE END | 
 |  | num. benef. | Budget | num. benef. | Budget | num. benef. | Budget | num. benef. | Budget
P01 | UNITOV | 6 | € 10,372.00 | 4 | € 5,430.00 | 0 | € 3,280.00 | 4 | € 5,430.00
P02 | UNISAPIENZA | 6 | € 8,540.00 | 0 | € - | 0 | € 8,540.00 | 0 | € -
P03 | NUUE | 8 | €41,096.00 | 8 | €40,704.00 |  | € 392.00 | 8 | € 40,704.00
P04 | LPNU | 8 | €40,566.00 | 8 | €35,336.00 |  | € 5,230.00 | 8 | € 35,336.00
P05 | ZSPU | 8 | €40,756.00 | 7 | €35,189.00 | 1 | € 5,567.00 | 11 | € 53,792.00
P06 | NTU | 8 | €40,756.00 | 8 | €40,658.00 |  | € 98.00 | 8 | € 40,658.00
P07 | GTU | 8 | €41,436.00 | 4 | €20,816.00 | 4 | €20,620.00 | 4 | € 20,816.00
P08 | BSMA | 8 | €41,436.00 | 4 | €21,432.00 | 4 | €20,004.00 | 4 | € 21,432.00
P09 | SUT | 12 | €31,504.00 | 9 | €23,762.00 | 6 | € 7,742.00 | 15 | € 39,782.00
P10 | IMPEER |  |  |  |  |  |  |  | 
P11 | HSW | 8 | €15,020.00 | 0 | € - | 8 | €15,020.00 | 8 | € 15,020.00
 |  |  | € 311,482.00 |  | € 223,327.00 |  | €86,493.00 |  | €272,970.00
 | PC |  | € 246,046.00 |  | € 194,135.00 |  | € 51,911.00 |  | € 212,738.00
 | ProgC |  | € 65,436.00 |  | € 29,192.00 |  | € 34,582.00 |  | € 60,232.00
SAVINGS € 86,493.00
PC: € 51,911.00
ProgC: € 36,244.00
Contractual obligations
PC: 48 vs 39 NOT YET RESPECTED
ProgC: 32 vs 13 NOT YET RESPECTED
Travels are not an weaknesses
but activities should be DONE
through e-learning/e-training

## Slide 18: WP 10 “Project management ……” B. Budget overview – SMS Staff 7
 |  | Staff mobility - GRANT |  | Staff mobility - DONE |  | Staff mobility - TO DO |  | Staff mobility - FORECAST TO THE END | 
 |  | num. benef. | Budget | num. benef. | Budget | num. benef. | Budget | num. benef. | Budget
P01 | UNITOV | 6 | €10,372.00 | 4 | € 5,430.00 | 0 | € 3,280.00 | 4 | € 5,430.00
P02 | UNISAPIENZA | 6 | € 8,540.00 | 0 | € - | 0 | € 8,540.00 | 0 | € -
P03 | NUUE | 8 | €41,096.00 | 8 | €40,704.00 |  | € 392.00 | 8 | € 40,704.00
P04 | LPNU | 8 | €40,566.00 | 8 | €35,336.00 |  | € 5,230.00 | 8 | € 35,336.00
P05 | ZSPU | 8 | € 40,756.00 | 7 | € 35,189.00 | 1 | € 5,567.00 | 11 | € 53,792.00
P06 | NTU | 8 | €40,756.00 | 8 | €40,658.00 |  | € 98.00 | 8 | € 40,658.00
P07 | GTU | 8 | €41,436.00 | 4 | €20,816.00 | 4 | €20,620.00 | 4 | € 20,816.00
P08 | BSMA | 8 | €41,436.00 | 4 | €21,432.00 | 4 | €20,004.00 | 4 | € 21,432.00
P09 | SUT | 12 | € 31,504.00 | 9 | € 23,762.00 | 6 | € 7,742.00 | 15 | € 39,782.00
P10 | IMPEER |  |  |  |  |  |  |  | 
P11 | HSW | 8 | € 15,020.00 | 0 | € - | 8 | € 15,020.00 | 8 | € 15,020.00
 |  |  | € 311,482.00 |  | € 223,327.00 |  | €86,493.00 |  | € 272,970.00
 | PC |  | € 246,046.00 |  | € 194,135.00 |  | € 51,911.00 |  | € 212,738.00
 | ProgC |  | € 65,436.00 |  | € 29,192.00 |  | € 36,244.00 |  | € 60,232.00
If travels return to be POSSIBLE
ZSPU, SUT and HSW stated their availability to travel

## Slide 19: WP 10 “Project management ……” B. Budget overview – SMS Staff+Students 8
Budget headings | num of beneficiaries | budget
Staff from Partner Countries | 43 (39 + 4) | € 212,738.00
Staff from Programme Countries | 27 (13 + 14) | € 60,232.00
Students from Partner Countries | 66 | € 240,038.00
Students from Programme Countries |  | 
Grant for Special Mobility Strand |  | € 513,008.00
GRANT |  | € 597,882.00
If travels return to be POSSIBLE
ZSPU, SUT and HSW stated their availability to travel
We received € 538,094 from EACEA.
Currently, we have to return € 25,086.00 (i.e. € 538,094 - € 513,008.00)

## Slide 20: WP 10 “Project management ……” B. Budget overview - CBHE 1

## Slide 21: WP 10 “Project management ……” B. Budget overview - CBHE 2
 |  | Staff costs (awarded) | 1. Staff costs (spent) | 4. Equipment Costs (awarded) | 4. Equipment Costs (spent) | 5. Subcontr Costs (awarded) | 5. Subcontr Costs (spent) | TOTAL (awarded) | TOTAL (spent)
P01 | UNITOV | € 110,050.00 | € 84,685.00 |  |  | € 34,740.00 | € 14,640.00 | € 157,000.00 | € 107,250.00
P02 | UNISAPIENZA | € 54,240.00 | € 13,088.00 |  |  |  |  | € 62,145.00 | € 15,953.00
P03 | NUUE | € 29,100.00 | € 27,780.00 | € 43,235.00 | € 40,944.79 |  |  | € 106,735.00 | € 97,034.79
P04 | LPNU | € 16,765.00 | € 16,765.00 | € 43,235.00 | € 16,335.46 |  |  | € 88,045.00 | € 54,885.46
P05 | ZSPU | € 17,670.00 | € 4,420.00 | € 43,235.00 | € 45,662.02 |  |  | € 89,830.00 | € 76,687.02
P06 | NTU | € 14,440.00 | € 6,294.00 | € 43,235.00 | € 18,831.00 |  |  | € 87,400.00 | € 48,710.00
P07 | GTU | € 12,960.00 | € 6,030.00 | € 43,235.00 | € 11,258.81 |  |  | € 86,705.00 | € 40,908.81
P08 | BSMA | € 11,715.00 | € 3,127.00 | € 43,235.00 | € 10,886.50 |  |  | € 86,655.00 | € 31,623.50
P09 | SUT | € 33,400.00 | € 17,950.00 |  |  |  |  | € 45,415.00 | € 23,550.00
P10 | IMPEER | € 9,600.00 | € 10,550.00 |  |  |  |  | € 20,450.00 | € 17,070.00
P11 | HSW | € 39,760.00 | € 29,610.00 |  |  |  |  | € 50,740.00 | € 37,260.00
 |  | € 349,700.00 | € 220,299.00 | € 259,410.00 | € 143,918.58 | € 34,740.00 | € 14,640.00 | € 881,120.00 | € 550,932.58
at 22nd of March 2021

## Slide 22: WP 10 “Project management ……” B. Budget overview - CBHE 3
Budget headings | 1. Grant Awarded (in EUR) | 2. Budget Spent at the end (in EUR)
1. Staff costs | € 349,700.00 | € 349,700.00
2. Travel costs | € 68,510.00 | € 50,155.00
3. Costs of Stay | € 168,760.00 | € 221,920.00
4. Equipment costs | € 259,410.00 | € 259,410.00
5. Subcontracting costs | € 34,740.00 | € 34,740.00
A. Grant for Project Activities | € 881,120.00 | € 815,925.00
We received € 793,008 from EACEA.
If travels continue to be not possible, we expect to receive € 22,917 from EACEA, at the end.
No further travels possible. FORECAST

## Slide 23: WP 10 “Project management ……” B. Budget overview - CBHE 4
If travels continue to be not possible
We have to return € 74,729 (SMS) - € 22,917 (CBHE)
€ 51,818

## Slide 24: WP 10 “Project management ……” B. Budget overview - CBHE 5
 |  | 1. Staff costs (awarded) | 2. Travel costs | 3. Costs of Stay | 4. Equipment Costs | 5. Subcontr Costs | TOTAL (awarded) | TOTAL (spent) | CBHE NOT USED
P01 | UNITOV | € 110,050.00 | € 3,005.00 | € 4,920.00 | € - | € 34,740.00 | € 157,000.00 | € 152,715.00 | 4,285.00 €
P02 | UNISAPIENZA | € 54,240.00 | € 1,185.00 | € 1,680.00 | € - | € - | € 62,145.00 | € 57,105.00 | 5,040.00 €
P03 | NUUE | € 29,100.00 | € 8,870.00 | € 19,440.00 | € 43,235.00 | € - | € 106,735.00 | € 100,645.00 | 6,090.00 €
P04 | LPNU | € 16,765.00 | € 5,585.00 | € 16,200.00 | € 43,235.00 | € - | € 88,045.00 | € 81,785.00 | 6,260.00 €
P05 | ZSPU | € 17,670.00 | € 7,045.00 | € 19,560.00 | € 45,662.02 | € - | € 89,830.00 | € 89,937.02 | - 107.02 €
P06 | NTU | € 14,440.00 | € 5,945.00 | € 17,640.00 | € 43,235.00 | € - | € 87,400.00 | € 81,260.00 | 6,140.00 €
P07 | GTU | € 12,960.00 | € 7,060.00 | € 16,560.00 | € 43,235.00 | € - | € 86,705.00 | € 79,815.00 | 6,890.00 €
P08 | BSMA | € 11,715.00 | € 4,890.00 | € 12,720.00 | € 43,235.00 | € - | € 86,655.00 | € 72,560.00 | 14,095.00 €
P09 | SUT | € 33,400.00 | € 1,640.00 | € 3,960.00 | € - | € - | € 45,415.00 | € 39,000.00 | 6,415.00 €
P10 | IMPEER | € 10,550.00 | € 2,200.00 | € 4,320.00 | € - | € - | € 20,450.00 | € 17,070.00 | 3,380.00 €
P11 | HSW | € 39,760.00 | € 2,730.00 | € 4,920.00 | € - | € - | € 50,740.00 | € 47,410.00 | 3,330.00 €
 | TOTALE | € 350,650.00 | € 50,155.00 | € 121,920.00 | € 261,837.02 | € 34,740.00 | € 881,120.00 | € 819,302.02 | 61,817.98 €
no further travel and Equipment purchases concluded

## Slide 25: WP 10 “Project management ……” B. Budget overview - SMS 6
 |  | SMS (awarded) | SMS (spent) | SMS NOT USED
P01 | UNITOV | € 12,034.00 | € 5,430.00 | € 6,604.00
P02 | UNISAPIENZA | € 8,540.00 | € - | € 8,540.00
P03 | NUUE | € 98,030.00 | € 98,030.00 | € -
P04 | LPNU | € 90,201.00 | € 89,659.00 | € 542.00
P05 | ZSPU | € 95,861.00 | € 82,476.00 | € 13,385.00
P06 | NTU | € 102,051.00 | € 94,835.00 | € 7,216.00
P07 | GTU | € 93,636.00 | € 43,141.00 | € 50,495.00
P08 | BSMA | € 52,667.00 | € 26,032.00 | € 26,635.00
P09 | SUT | € 31,504.00 | € 23,762.00 | € 7,742.00
P10 | IMPEER | € - | € - | € -
P11 | HSW | € 15,020.00 | € - | € 15,020.00
 | TOTALE | € 599,544.00 | € 463,365.00 | € 136,179.00
no further travels

## Slide 26: WP 10 “Project management ……” B. Budget overview – CBHE + SMS 7
 |  | GRANT (awarded) | GRANT (spent) | GRANT NOT USED
P01 | UNITOV | € 169,034.00 | € 158,145.00 | € 10,889.00
P02 | UNISAPIENZA | € 70,685.00 | € 57,105.00 | € 13,580.00
P03 | NUUE | € 204,765.00 | € 198,675.00 | € 6,090.00
P04 | LPNU | € 178,246.00 | € 171,444.00 | € 6,802.00
P05 | ZSPU | € 185,691.00 | € 172,413.02 | € 13,277.98
P06 | NTU | € 189,451.00 | € 176,095.00 | € 13,356.00
P07 | GTU | € 180,341.00 | € 122,956.00 | € 57,385.00
P08 | BSMA | € 139,322.00 | € 98,592.00 | € 40,730.00
P09 | SUT | € 76,919.00 | € 62,762.00 | € 14,157.00
P10 | IMPEER | € 20,450.00 | € 17,070.00 | € 3,380.00
P11 | HSW | € 65,760.00 | € 47,410.00 | € 18,350.00
 | TOTALE | € 1,480,664.00 | € 1,282,667.02 | € 197,996.98
no further travel and Equipment purchases concluded
Remember: co-financing: overhead costs, bank charges, etc.

## Slide 27: WP 10 “Project management ……” B. How to continue after eligibility period: new proposals?
We can manage for sending coordinator short description on how each institution would like to continue SmaLog. SmaLog II?